## Dr. Neeraja
S.NO | Changes | Category | Change Status | Testing Status | Comment
1 | Branch changing option (past billings should not change) | Major | DONE | DONE | right now open option is given where who creates the package can select which branch payment will be mapped
2 | AMR number long series is being generated need to shorten it also make UTR number mandatory for all transactions except Cash.Bajaj | Major
3 | Payment, billings must reflect with the branch they have visited. | Major | partially done | DONE | right now open option is given where who creates the package can select which branch payment will be mapped
4 | In case sheet need to add mandatory medicine days. Case sheet needs to be open in a new tab. | Minor
5 | In case sheet for old patients need other options as collapsible. | Minor
6 | Order should be like this
7 | Clinical Observation
8 | Prescription with medicine days, follow up date etc (rest all collapsible)
9 | In case sheet all text formatting should work. Eg- Bold, italics, underline, color etc. after submitting | Major
10 | When creating on appointment. Invoices are getting generated with zero payment and zero paid. | Minor
11 | If paid appointment has been booked for a patient and paid as well, while generating the second appointment it must show a message consultation fee has already been taken, Do want to proceed. | Minor
12 | Reports
| a.Enquiry GT Report | Major
| b.Renewal Report | Major
| c.Payment details report showing multiple packages for part payment. | Major
| d. GT report (as per excel sheet shared) | Major
| e.Target assigning option branch wise and employee wise/role wise. | Major
13 | For service doctors. On appointment has to be fixed .also treatment. | Minor | done | done
14 | In token system courier and other appointments are also being shown if booked for the particular doctor. Hence also S.no is showing different. | Major
15 | After case sheet is created and also prescription is added from doctor. only after validation from PRO it should go to pharmacy. Also need to add PRO comment even if package is created or not. | Minor
16 | In overview need to show alternative number and also consultation fee | Minor | done | done
17 | Need to add detailed log for patient’s module also. | Major
18 | Click guard for payments. Still multiple payments are being generated. | Major
19 | In the appointments table. Need to give filter for appointment type.-Minor | Minor | done | done
20 | Call follow ups need to show in home branch.
21 | Age auto updation for patients. | Major
22 | Latest medicine end date must shown in the patient overview part. | Minor | done | done
23 | While updating the payments info for the partial paid payment. Updation is taking time.

## Branch Doctors
S.NO | Changes | Status | Comment
1 | Treatment duration suggested by doctor should be displayed as per old entry the very first visit of the patient. | Not completed | script was stopped
2 | Presenting complaints and complaints has to be visible . | Not completed | script was stopped
3 | Text formatting in the case sheet must work after submission | Not started
4 | Apart from Clinincal observation and presenting complaints and history and prescription..all fields must be collapsible in the case sheet | Not started
5 | Case sheet should open in new tab(view and create both).If any field in empty in the prescription then values are shifting to blank fields | Not started
6 | Token system must not show appointment like DR TALK Appointment ,Courier appointments. | Not started

## Akila
Changes | Category | Change Status | Testing Status
Bifurcation of consultation fee and package in the reports | Minor | Pending | Pending
Multiselect and select all in all reports | Major | Pending | Pending

## Sunita
Changes | Category | Change Status | Testing Status | Comment
MR number search | Minor | Done | Done
Alternate Number search | Minor | Done | Done
In patient overview medicine end date | Minor | Done | Done | based upon missed medicine date must be updated
GT report | Major | Pending
Renewal report | Major | Pending
Branch and executive target assigning | Major | Pending |  | future
Add payment type in payment details report and also while doing payment | Minor | Pending

## Ramesh
S.NO |  | Status | Comment
1 | PRO validation before showing prescription at Pharmacy |  | Future